## Read Me
Beauty / Salon / Barbershop SaaS Development Plan
Purpose | Step-by-step development plan for a multi-tenant SaaS platform supporting beauty parlours, salons, barbershops, spas, and similar service businesses.
How to use | Start with the 'Roadmap' sheet for phases, then use 'Detailed Plan' to execute module-by-module tasks. Update owner, status, and target week as the project progresses.
Assumption | Plan is structured for MVP first, then scale and optimization. Timeline is expressed in relative weeks so you can adapt it to your team size.
Suggested team | Product Manager, Business Analyst, UX/UI Designer, Backend Engineer(s), Frontend Web Engineer, Mobile Engineer, QA Engineer, DevOps Engineer.
Primary stack | PostgreSQL, API layer, web admin/merchant portal, customer app/web, notification service, payment integration, map/geolocation integration.
Sheets | Read Me ¦ Roadmap ¦ Detailed Plan ¦ Milestones ¦ Team Plan ¦ Risks & Dependencies

## Roadmap
Phase No | Phase | Objective | Major Deliverables | Estimated Duration (Weeks) | Depends On
1 | Discovery & Product Definition | Finalize business scope, MVP, non-functional requirements, personas, and release strategy. | Vision, PRD, feature list, scope baseline, success metrics | 2 | -
2 | Solution Architecture & UX | Define architecture, data model, APIs, tenant model, and customer/merchant/admin UX. | Architecture doc, ERD, API outline, wireframes, design system | 3 | Phase 1
3 | Platform Foundation | Set up repos, environments, CI/CD, auth, RBAC, tenancy, observability, and basic infrastructure. | Dev environment, auth module, tenant base, CI/CD pipelines | 3 | Phase 2
4 | Merchant & Catalog Modules | Build business onboarding, branches, staff, services, pricing, schedules, and settings. | Merchant portal MVP, catalog module, branch management | 4 | Phase 3
5 | Customer Discovery & Booking | Build location search, nearest shops, profile pages, availability, booking, and notifications. | Customer booking flow, slot engine, booking APIs, reminders | 5 | Phase 4
6 | Payments, Reviews & CRM | Add payments, reviews, favorites, promotions, loyalty basics, and customer engagement. | Payment integration, review system, promotions MVP | 4 | Phase 5
7 | Admin, QA & UAT | Build admin controls, reporting basics, security checks, full QA, performance tests, UAT, and fixes. | Admin portal, test sign-off, UAT sign-off, release checklist | 4 | Phase 6
8 | Production Launch & Stabilization | Deploy production, monitor live usage, fix early issues, and optimize operations. | Go-live, monitoring dashboards, support runbook, hotfix plan | 2 | Phase 7
9 | Phase 2 Enhancements | Scale with memberships, POS, inventory, home service, analytics, and multi-branch optimization. | Growth roadmap modules | 6 | Phase 8

## Detailed Plan
Seq | Phase | Module | Task | Deliverable | Owner | Priority | Est. Weeks | Target Start Week | Target End Week | Status | Dependencies
1 | Discovery | Business Analysis | Identify user types: customer, merchant, staff, platform admin. | User role matrix | BA/Product | High | 1 | 1 |  | Not Started | -
2 | Discovery | Business Analysis | Finalize business categories: beauty parlour, barber, salon, spa, nail studio, makeup artist, grooming studio. | Category scope | BA/Product | High | 1 | 1 |  | Not Started | -
3 | Discovery | Requirements | Document MVP and Phase 2 features. | Feature baseline | Product | High | 1 | 1 |  | Not Started | Task 1
4 | Discovery | Requirements | Define user journeys for search, booking, reschedule, cancel, review, merchant onboarding. | Journey maps | BA/UX | High | 1 | 2 |  | Not Started | Task 3
5 | Discovery | NFR | Define performance, security, tenancy, audit, backup, privacy, and scale requirements. | NFR document | Architect | High | 1 | 2 |  | Not Started | Task 3
6 | Architecture | Architecture | Define system architecture for web, mobile, API, PostgreSQL, cache, notifications, payments, maps. | Architecture diagram | Architect | High | 1 | 3 |  | Not Started | Phase Discovery
7 | Architecture | Data Design | Finalize ERD and core schemas for tenant, user, merchant, services, booking, payments. | ERD baseline | Architect/DB | High | 1 | 3 |  | Not Started | Task 6
8 | Architecture | API Design | Prepare API contract for auth, merchant, catalog, search, booking, payment, review, admin. | API specification | Architect/Backend | High | 1 | 3 |  | Not Started | Task 6
9 | Architecture | UX | Design customer app wireframes. | Customer wireframes | UX | High | 1 | 3 |  | Not Started | Task 4
10 | Architecture | UX | Design merchant dashboard wireframes. | Merchant wireframes | UX | High | 1 | 4 |  | Not Started | Task 4
11 | Architecture | UX | Design platform admin wireframes. | Admin wireframes | UX | Medium | 1 | 4 |  | Not Started | Task 4
12 | Foundation | DevOps | Create repositories, branching strategy, environments, CI/CD. | Working pipelines | DevOps | High | 1 | 5 |  | Not Started | Phase Architecture
13 | Foundation | Security | Implement authentication, token flow, password rules, session handling. | Auth module | Backend | High | 1 | 5 |  | Not Started | Task 8
14 | Foundation | Security | Implement RBAC for customer, merchant owner, branch manager, staff, admin. | RBAC | Backend | High | 1 | 5 |  | Not Started | Task 13
15 | Foundation | Tenancy | Implement tenant setup, subscription base, tenant settings. | Tenant foundation | Backend | High | 1 | 5 |  | Not Started | Task 7
16 | Foundation | Observability | Set up logging, metrics, tracing, error monitoring, audit logging. | Observability baseline | DevOps/Backend | Medium | 1 | 6 |  | Not Started | Task 12
17 | Merchant | Onboarding | Merchant registration, KYC/business verification, business type selection. | Merchant onboarding | Backend/Web | High | 1 | 6 |  | Not Started | Task 15
18 | Merchant | Branch Management | Create branch CRUD, address, maps, hours, holidays, closures. | Branch module | Backend/Web | High | 1 | 6 |  | Not Started | Task 17
19 | Merchant | Staff Management | Create staff profile, skill mapping, schedules, leaves, breaks. | Staff module | Backend/Web | High | 1 | 7 |  | Not Started | Task 18
20 | Merchant | Catalog | Create service categories, services, variants, addons, bundles. | Catalog base | Backend/Web | High | 1 | 7 |  | Not Started | Task 18
21 | Merchant | Pricing | Create branch-specific service pricing and duration rules. | Pricing module | Backend/Web | High | 1 | 7 |  | Not Started | Task 20
22 | Merchant | Availability | Implement staff and branch availability model. | Availability base | Backend | High | 1 | 8 |  | Not Started | Task 19
23 | Merchant | Media | Upload shop gallery, service images, staff images, documents. | Media module | Backend/Web | Medium | 1 | 8 |  | Not Started | Task 17
24 | Customer | Discovery | Integrate geolocation and nearest branch search. | Location search | Backend/App | High | 1 | 8 |  | Not Started | Task 18
25 | Customer | Search | Implement filters: category, service, price, distance, rating, open now, available now. | Search filters | Backend/App | High | 1 | 9 |  | Not Started | Task 24
26 | Customer | Shop Profile | Build business/branch profile pages with services, timing, staff, photos, reviews. | Shop profile | Backend/App | High | 1 | 9 |  | Not Started | Task 23
27 | Booking | Slot Engine | Build slot generation using branch hours, staff schedules, leaves, and service duration. | Slot engine | Backend | High | 2 | 9 |  | Not Started | Task 22
28 | Booking | Appointment | Implement create booking, multi-service booking, preferred staff selection. | Booking module | Backend/App | High | 1 | 10 |  | Not Started | Task 27
29 | Booking | Appointment Lifecycle | Implement confirm, reschedule, cancel, no-show, completed states. | Appointment workflow | Backend/Web/App | High | 1 | 10 |  | Not Started | Task 28
30 | Booking | Notifications | Integrate confirmation, reminder, cancellation notifications. | Notification flows | Backend | High | 1 | 10 |  | Not Started | Task 28
31 | Booking | Merchant Calendar | Build merchant calendar/day schedule and appointment management UI. | Merchant calendar | Web | High | 1 | 11 |  | Not Started | Task 29
32 | Payments | Checkout | Support pay-at-shop and online payment options. | Checkout MVP | Backend/App/Web | High | 1 | 11 |  | Not Started | Task 28
33 | Payments | Gateway | Integrate payment gateway, payment callback, transaction logs, refunds. | Payment integration | Backend | High | 1 | 11 |  | Not Started | Task 32
34 | CRM | Reviews | Implement ratings, reviews, merchant replies, moderation flags. | Review module | Backend/App/Web | Medium | 1 | 12 |  | Not Started | Task 29
35 | CRM | Favorites | Implement favorites, saved shops, repeat booking shortcuts. | Favorites module | Backend/App | Medium | 1 | 12 |  | Not Started | Task 26
36 | CRM | Promotions | Implement promo codes and campaign support. | Promotions MVP | Backend/Web/App | Medium | 1 | 12 |  | Not Started | Task 32
37 | Admin | Merchant Ops | Build admin screens for merchant approvals and verification. | Admin merchant ops | Web/Backend | High | 1 | 13 |  | Not Started | Task 17
38 | Admin | Catalog Control | Admin management of business types, categories, and master settings. | Admin masters | Web/Backend | Medium | 1 | 13 |  | Not Started | Task 20
39 | Admin | Issue Management | Support complaints, disputes, tickets, and review moderation. | Support module | Web/Backend | Medium | 1 | 13 |  | Not Started | Task 34
40 | Admin | Platform Reports | Create basic dashboards for bookings, merchants, revenue, customer growth. | KPI dashboards | Web/Backend | Medium | 1 | 14 |  | Not Started | Task 33
41 | Quality | Testing | Write unit, integration, API, UI, and regression test cases. | Test suite | QA | High | 2 | 14 |  | Not Started | Parallel
42 | Quality | Security | Run security review for auth, payment, API access, tenant isolation. | Security report | QA/Security | High | 1 | 15 |  | Not Started | Task 13
43 | Quality | Performance | Load test search, booking, slot engine, and payment callbacks. | Performance report | QA/DevOps | High | 1 | 15 |  | Not Started | Task 27
44 | Release | UAT | Conduct UAT with sample merchants and customers. | UAT sign-off | Product/QA | High | 1 | 16 |  | Not Started | Phase Quality
45 | Release | Go-Live | Deploy production, smoke test, enable monitoring and support process. | Production launch | DevOps/Product | High | 1 | 16 |  | Not Started | Task 44
46 | Release | Hypercare | Track incidents, hotfixes, user feedback, and priority optimizations. | Hypercare report | All | High | 2 | 17 |  | Not Started | Task 45
47 | Phase 2 | Memberships | Add membership plans, wallet, loyalty points, gift cards. | Membership & loyalty | Backend/Web/App | Medium | 2 | 19 |  | Not Started | Task 46
48 | Phase 2 | Operations | Add POS, inventory, product sales, suppliers, stock movements. | POS & inventory | Backend/Web | Medium | 3 | 19 |  | Not Started | Task 46
49 | Phase 2 | Home Service | Support at-home bookings, service zones, travel fees, visit tracking. | Home service | Backend/App/Web | Medium | 2 | 20 |  | Not Started | Task 46
50 | Phase 2 | Analytics | Advanced analytics, cohort analysis, customer retention, merchant intelligence. | Advanced analytics | Backend/Web | Low | 2 | 21 |  | Not Started | Task 40

## Milestones
Milestone | Description | Planned Week | Success Criteria
M1: Scope Signed Off | Scope, features, MVP, and business goals approved. | 2 | All stakeholders approve scope
M2: Architecture Approved | Architecture, ERD, APIs, and UX baseline approved. | 4 | Architecture review complete
M3: Foundation Complete | Auth, tenancy, CI/CD, environments, logging ready. | 6 | Dev baseline usable by all teams
M4: Merchant Modules Ready | Merchant onboarding, branches, staff, services ready. | 8 | Merchant can fully configure business
M5: Customer Booking Ready | Search, nearest shop, slot engine, booking flow operational. | 11 | End-to-end booking works
M6: Payment & CRM Ready | Payments, reviews, and promo code basics ready. | 12 | Payment test cases pass
M7: UAT Sign-Off | Business UAT successfully completed. | 16 | Signed UAT checklist
M8: Production Go-Live | System released to live production. | 16 | Go-live sign-off complete
M9: Hypercare Complete | Initial post-launch issues addressed. | 18 | Critical incidents closed

## Team Plan
Role | Main Responsibilities | Recommended Allocation | When Needed Most
Product Manager | Scope, backlog, priorities, stakeholder alignment, UAT. | 1 Full Time | Weeks 1-18
Business Analyst | Requirements, workflows, user stories, acceptance criteria. | 1 Full Time | Weeks 1-8
Solution Architect | Architecture, NFRs, data design, API standards. | 1 Part/Full Time | Weeks 1-8
UX/UI Designer | Wireframes, journeys, interaction design, design system. | 1 Full Time | Weeks 1-8
Backend Engineer | API, auth, tenancy, booking, payments, notifications, admin. | 2-3 Full Time | Weeks 5-18
Frontend Web Engineer | Merchant portal, admin portal, dashboards. | 1-2 Full Time | Weeks 6-18
Mobile/App Engineer | Customer app or customer web/mobile experience. | 1-2 Full Time | Weeks 8-18
QA Engineer | Test strategy, automation, regression, UAT support. | 1-2 Full Time | Weeks 10-18
DevOps Engineer | CI/CD, infra, monitoring, deployment, rollback, support. | 1 Part/Full Time | Weeks 5-18

## Risks & Dependencies
Type | Item | Impact | Mitigation
Risk | Unclear pricing/business rules across different shop types | Delays data model and catalog design | Freeze common rules first; use configurable pricing models
Risk | Complex availability logic for multiple staff/services | Can delay booking engine | Release MVP with simpler slot rules, then optimize
Risk | Payment gateway or map API delays | Blocks booking/payment go-live | Start integrations early with sandbox access
Risk | Tenant isolation/security gaps | Critical production risk | Design tenant filtering and security review from foundation phase
Risk | Poor data quality during merchant onboarding | Bad customer experience | Use validation, required fields, and admin approval
Dependency | Merchant KYC/legal rules | Needed for onboarding design | Confirm operational policy before implementation
Dependency | Map/geolocation provider | Needed for nearest shop logic | Select provider during architecture phase
Dependency | Notification provider | Needed for OTP and reminders | Choose SMS/email/push vendors early
Dependency | Payment provider | Needed for online payments/refunds | Secure test credentials before phase 6